SECOND AMENDMENT TO

PUBLIC IMPROVEMENTS AGREEMENT

FOR RODEO MARINA SEWER EXPANSION

This Second Amendment to Public Improvements Agreement for Rodeo Marina Sewer Expansion (the "Second Amendment") is entered as of December ____, 2012 by and between the Successor Agency to the former Contra Costa County Redevelopment Agency, a separate public entity (the "Successor Agency") and the Rodeo Sanitary District (the "District”), based on the following facts, understandings, and intentions of the parties:

RECITALS

# The Contra Costa County Redevelopment Agency (the "Dissolved RDA") and the District entered into that certain Public Improvements Agreement for Rodeo Marina Sewer Expansion, dated as of December 14, 2010, as amended by that certain First Amendment to Public Improvement Agreement for Rodeo Marina Sewer Expansion, dated as of _________, (collectively the "Public Improvement Agreement").  Capitalized terms used in this Second Amendment, but not separately defined herein, have the meaning set forth in the Public Improvement Agreement.

- On February 1, 2012, pursuant to AB1x 26 (the “Dissolution Act”) the Dissolved RDA, along with all redevelopment agencies in the State of California, was dissolved, and all assets and obligations of the RDA were transferred by operation of law to the Successor Agency.

# The Public Improvement Agreement evidences an Infrastructure Grant to the District in an amount not to exceed One Million Five Hundred Fifty Nine Thousand Dollars ($1,559,000) to pay for the costs of designing and constructing the Sewer Improvements and to complete the Infrastructure Program.

# The budget for the Infrastructure Program must be further revised to reflect an increase of construction costs of approximately One Hundred Seventy-Five Thousand Dollars ($175,000) to fund additional construction work resulting from the discovery of adverse conditions during excavation and construction of the project.  The revised total budget for the Infrastructure Program is now estimated to be One Million Seven Hundred Thirty-Four Thousand Dollars ($1,734,000) (the “Revised Budget”).

# The Successor Agency and District now desire to amend the Public Improvement Agreement to increase the amount of the Infrastructure Grant to a reflect the Revised Budget amount, and to extend the completion deadline to reflect the additional work that must now be completed, which was not anticipated in the previous project schedule.

NOW, THEREFORE, the Successor Agency and the District agree as follows:

Section 1.1	Infrastructure Grant.   The amount of the Infrastructure Grant as set forth in Section 1.2(a) of the Public Improvement Agreement is increased from One Million Five Hundred Fifty Nine Thousand Dollars ($1,559,000) to One Million Seven Hundred Thirty-Four Thousand Dollars ($1,734,000).

Section 1.2	Approved Budget.  The Revised Budget attached to the Public Improvement Agreement as Exhibit A is hereby revised to reflect the increase in the in the total grant amount from One Million Five Hundred Fifty Nine Thousand Dollars ($1,559,000) to One Million Seven Hundred Thirty-Four Thousand Dollars ($1,734,000).  Other than the changes identified in this Second Amendment, the Revised Budget remains unchanged.

Section 1.3	Project Schedule.  The completion date referred to in Section 1.6 of the Public Improvement Agreement and the Revised Schedule is further revised from December 31, 2012 to December 31, 2013, granting a twelve month extension to complete the additional work contemplated hereunder.

Section 1.4	No Other Changes to the Agreement.  Except as expressly modified by this Second Amendment, all other provisions of the Public Improvement Agreement remain unmodified and continue in full force and effect.

Section 1.5	Conflicts with the Agreement.  In the event of any conflict between this Second Amendment and the Public Improvement Agreement, the provisions of this Second Amendment shall prevail.

Section 1.6	Counterparts; Multiple Originals.  This Second Amendment may be executed in multiple originals, each of which is deemed to be an original, and may be signed in counterparts.

Section 1.7	Effectiveness.  This Second Amendment shall take effect subject to the Successor Agency receiving all necessary approvals required under the Dissolution Act.

Remainder of Page Left Intentionally Blank

IN WITNESS WHEREOF, this First Amendment has been executed as of the date set forth in the opening paragraph of this First Amendment.

CONTRA COSTA COUNTY SUCCESSOR AGENCY, a separate public entity

By: __________________________________

Its: __________________________________

RODEO SANITARY DISTRICT

By: __________________________________

Its: __________________________________